## roadmap
Task ID | Task Name | Description | Category | Status | Priority | Assignee | Start Date | Due Date | Dependencies
PHASE-1 | PHASE 1: REQUIREMENTS ANALYSIS AND PLANNING | 4 WEEKS duration | Planning | Not Started | High | Project Manager | 2025-05-01 | 2025-05-28
RA-001 | Market Analysis | Conduct market analysis and competitor research | Research | Not Started | High | Product Manager | 2025-05-01 | 2025-05-14
RA-002 | Feature Requirements Documentation | Document all feature requirements | Documentation | Not Started | High | Product Manager | 2025-05-01 | 2025-05-21
RA-003 | Technical Specification Development | Develop technical specifications | Documentation | Not Started | High | Tech Lead | 2025-05-08 | 2025-05-21 | RA-002
RA-004 | Project Planning | Create project plan and timeline | Planning | Not Started | High | Project Manager | 2025-05-15 | 2025-05-28 | RA-002
RA-005 | Resource Allocation | Allocate resources for the project | Planning | Not Started | Medium | Project Manager | 2025-05-15 | 2025-05-28 | RA-004
RA-006 | Risk Assessment | Identify and document potential risks | Planning | Not Started | Medium | Project Manager | 2025-05-15 | 2025-05-28
RA-007 | Risk Mitigation Planning | Develop risk mitigation strategies | Planning | Not Started | Medium | Project Manager | 2025-05-22 | 2025-05-28 | RA-006
RA-008 | Finalize Feature List | Complete and approve final feature list | Planning | Not Started | High | Product Manager | 2025-05-22 | 2025-05-28 | RA-002
RA-009 | Initial Architecture Design | Develop initial architectural design | Design | Not Started | High | Tech Lead | 2025-05-15 | 2025-05-28 | RA-003
PHASE-2 | PHASE 2: SYSTEM DESIGN | 6 WEEKS duration | Design | Not Started | High | Tech Lead | 2025-05-29 | 2025-07-09 | PHASE-1
SD-001 | Architecture Design | Create detailed system architecture design | Design | Not Started | High | Tech Lead | 2025-05-29 | 2025-06-12 | RA-009
SD-002 | Architecture Documentation | Document the system architecture | Documentation | Not Started | High | Tech Lead | 2025-06-06 | 2025-06-19 | SD-001
SD-003 | Database Schema Design | Design database schema | Design | Not Started | High | Database Engineer | 2025-05-29 | 2025-06-19 | RA-009
SD-004 | UI/UX Wireframing | Create wireframes for all major screens | Design | Not Started | High | UI/UX Designer | 2025-05-29 | 2025-06-19 | RA-008
SD-005 | UI/UX Prototyping | Develop interactive prototypes | Design | Not Started | High | UI/UX Designer | 2025-06-13 | 2025-07-02 | SD-004
SD-006 | API Design | Design API endpoints and documentation | Design | Not Started | High | Backend Developer | 2025-06-06 | 2025-06-26 | SD-001
SD-007 | Security Architecture Planning | Plan security architecture | Security | Not Started | High | Security Engineer | 2025-06-13 | 2025-07-02 | SD-001
SD-008 | Development Environment Setup | Set up development environment | DevOps | Not Started | Medium | DevOps Engineer | 2025-06-27 | 2025-07-09 | SD-001
PHASE-3 | PHASE 3: IMPLEMENTATION | 14 WEEKS duration | Development | Not Started | High | Tech Lead | 2025-07-10 | 2025-10-15 | PHASE-2
PHASE-3.1 | Core Features Implementation | Implementation of core features | Development | Not Started | High | Tech Lead | 2025-07-10 | 2025-08-28 | PHASE-2
IM-001 | Frontend Setup | Set up React.js with TypeScript project structure | Development | Not Started | High | Frontend Developer | 2025-07-10 | 2025-07-16 | SD-005
IM-002 | State Management Setup | Implement Redux Toolkit for state management | Development | Not Started | High | Frontend Developer | 2025-07-10 | 2025-07-23 | IM-001
IM-003 | Styling Framework Setup | Set up Tailwind CSS and Headless UI | Development | Not Started | Medium | Frontend Developer | 2025-07-10 | 2025-07-23 | IM-001
IM-004 | User Authentication System | Implement user authentication with Auth0 | Development | Not Started | High | Backend Developer | 2025-07-10 | 2025-07-30 | SD-006
IM-005 | Database Implementation | Set up Supabase database according to schema | Development | Not Started | High | Database Engineer | 2025-07-10 | 2025-07-30 | SD-003
IM-006 | Core UI Components | Develop reusable UI components | Development | Not Started | High | Frontend Developer | 2025-07-17 | 2025-08-07 | IM-003
IM-007 | Color Palette Generator | Implement core palette generation feature | Development | Not Started | High | Frontend Developer | 2025-07-24 | 2025-08-21 | IM-006
IM-008 | Color Manipulation Tools | Implement color adjustment tools | Development | Not Started | High | Frontend Developer | 2025-07-31 | 2025-08-28 | IM-007
IM-009 | Database Integration | Integrate frontend with database | Development | Not Started | High | Full Stack Developer | 2025-07-24 | 2025-08-14 | IM-005
PHASE-3.2 | Advanced Features Implementation | Implementation of advanced features | Development | Not Started | High | Tech Lead | 2025-08-29 | 2025-10-15 | PHASE-3.1
IM-010 | Palette Management Features | Implement save, edit, delete functionality | Development | Not Started | High | Full Stack Developer | 2025-08-29 | 2025-09-11 | IM-009
IM-011 | Export Functionality | Implement various export options | Development | Not Started | Medium | Frontend Developer | 2025-08-29 | 2025-09-18 | IM-007
IM-012 | Community Features | Implement like, comment, follow features | Development | Not Started | Medium | Full Stack Developer | 2025-09-05 | 2025-09-25 | IM-010
IM-013 | API Endpoints | Develop RESTful API endpoints | Development | Not Started | High | Backend Developer | 2025-09-12 | 2025-10-01 | IM-009
IM-014 | Color Tools Implementation | Implement color blindness simulator and contrast checker | Development | Not Started | Medium | Frontend Developer | 2025-09-12 | 2025-10-01 | IM-008
IM-015 | Exploration Tools | Implement browse and filter functionality | Development | Not Started | Medium | Frontend Developer | 2025-09-26 | 2025-10-15 | IM-012
IM-016 | Integration Features | Implement image color extraction | Development | Not Started | Low | Full Stack Developer | 2025-10-02 | 2025-10-15 | IM-011
PHASE-3.3 | Testing Implementation | Implementation of testing | Testing | Not Started | High | QA Engineer | 2025-07-17 | 2025-11-06 | PHASE-3.1
IM-017 | Unit Testing Setup | Set up Jest for JavaScript/TypeScript | Testing | Not Started | High | QA Engineer | 2025-07-17 | 2025-07-23 | IM-001
IM-018 | Component Testing | Implement React Testing Library tests | Testing | Not Started | High | Frontend Developer | 2025-07-24 | 2025-08-14 | IM-006
IM-019 | API Testing | Implement API endpoint tests | Testing | Not Started | High | Backend Developer | 2025-09-19 | 2025-10-08 | IM-013
IM-020 | Integration Tests | Develop integration tests | Testing | Not Started | High | QA Engineer | 2025-10-09 | 2025-11-06 | IM-015
PHASE-4 | PHASE 4: TESTING | 4 WEEKS duration | Testing | Not Started | High | QA Engineer | 2025-10-16 | 2025-11-13 | PHASE-3
TS-001 | System Testing | Conduct end-to-end system testing | Testing | Not Started | High | QA Engineer | 2025-10-16 | 2025-10-29 | IM-020
TS-002 | Performance Testing | Test application performance and optimization | Testing | Not Started | High | Performance Engineer | 2025-10-23 | 2025-11-06 | TS-001
TS-003 | Security Testing | Conduct security vulnerability testing | Testing | Not Started | High | Security Engineer | 2025-10-23 | 2025-11-06 | TS-001
TS-004 | Accessibility Testing | Test for WCAG compliance | Testing | Not Started | High | Accessibility Specialist | 2025-10-30 | 2025-11-13 | TS-001
TS-005 | Bug Fixing and Refinement | Fix identified issues and refine features | Development | Not Started | High | Development Team | 2025-10-16 | 2025-11-13 | TS-001
TS-006 | Final System Testing | Conduct final system testing after fixes | Testing | Not Started | High | QA Engineer | 2025-11-14 | 2025-11-27 | TS-005
PHASE-5 | PHASE 5: DEPLOYMENT | 2 WEEKS duration | Deployment | Not Started | High | DevOps Engineer | 2025-11-14 | 2025-12-10 | PHASE-4
DP-001 | CI/CD Pipeline Setup | Set up continuous integration and deployment pipeline | DevOps | Not Started | High | DevOps Engineer | 2025-11-14 | 2025-11-27 | TS-006
DP-002 | Staging Environment Deployment | Deploy application to staging environment | DevOps | Not Started | High | DevOps Engineer | 2025-11-21 | 2025-11-27 | DP-001
DP-003 | Production Environment Preparation | Prepare production environment | DevOps | Not Started | High | DevOps Engineer | 2025-11-21 | 2025-12-03 | DP-002
DP-004 | Documentation Finalization | Complete all documentation | Documentation | Not Started | Medium | Technical Writer | 2025-11-14 | 2025-12-03 | TS-006
DP-005 | Deployment Checklist Verification | Verify all deployment requirements | DevOps | Not Started | High | Project Manager | 2025-11-28 | 2025-12-03 | DP-003
DP-006 | Soft Launch | Conduct beta testing with limited users | Deployment | Not Started | High | Project Manager | 2025-11-28 | 2025-12-10 | DP-005
DP-007 | Performance Monitoring Setup | Set up monitoring and alerting | DevOps | Not Started | Medium | DevOps Engineer | 2025-11-28 | 2025-12-10 | DP-003
DELIV-1 | DOCUMENTATION DELIVERABLES | Documentation deliverables | Documentation | Not Started | High | Technical Writer | 2025-05-08 | 2025-12-03
DOC-001 | Project Requirements Document | Create comprehensive project requirements document | Documentation | Not Started | High | Product Manager | 2025-05-08 | 2025-05-28 | RA-002
DOC-002 | Technical Architecture Documentation | Document technical architecture | Documentation | Not Started | High | Tech Lead | 2025-06-13 | 2025-07-02 | SD-002
DOC-003 | API Documentation | Create API documentation | Documentation | Not Started | High | Backend Developer | 2025-09-26 | 2025-10-15 | IM-013
DOC-004 | User Guide | Create user guide and help documentation | Documentation | Not Started | Medium | Technical Writer | 2025-10-30 | 2025-11-27 | TS-001
DOC-005 | Accessibility Compliance Documentation | Document accessibility compliance | Documentation | Not Started | Medium | Accessibility Specialist | 2025-11-07 | 2025-11-27 | TS-004
DOC-006 | Development Standards Document | Create development standards document | Documentation | Not Started | Medium | Tech Lead | 2025-06-20 | 2025-07-09 | SD-002
DOC-007 | Testing Strategy Document | Create testing strategy document | Documentation | Not Started | Medium | QA Engineer | 2025-07-17 | 2025-07-30 | IM-017
DOC-008 | Deployment Procedure Documentation | Document deployment procedures | Documentation | Not Started | Medium | DevOps Engineer | 2025-11-21 | 2025-12-03 | DP-002
DELIV-2 | DESIGN DELIVERABLES | Design deliverables | Design | Not Started | High | UI/UX Designer | 2025-06-06 | 2025-07-16
DES-001 | Brand Identity Guidelines | Create brand identity guidelines | Design | Not Started | Medium | UI/UX Designer | 2025-06-06 | 2025-06-26 | SD-004
DES-002 | UI Component Library | Develop UI component library | Design | Not Started | High | UI/UX Designer | 2025-06-20 | 2025-07-16 | SD-005
DES-003 | Wireframes | Create wireframes for all major screens | Design | Not Started | High | UI/UX Designer | 2025-05-29 | 2025-06-19 | SD-004
DES-004 | Interactive Prototypes | Develop interactive prototypes | Design | Not Started | High | UI/UX Designer | 2025-06-13 | 2025-07-02 | DES-003
DES-005 | Responsive Design Specifications | Create responsive design specifications | Design | Not Started | High | UI/UX Designer | 2025-06-20 | 2025-07-09 | DES-003
DES-006 | Animation and Transition Specifications | Document animation and transition specifications | Design | Not Started | Low | UI/UX Designer | 2025-06-27 | 2025-07-16 | DES-004
DES-007 | Accessibility Design Guidelines | Create accessibility design guidelines | Design | Not Started | High | Accessibility Specialist | 2025-06-20 | 2025-07-09 | DES-003
DES-008 | Color System Documentation | Document color system | Design | Not Started | Medium | UI/UX Designer | 2025-06-13 | 2025-07-02 | DES-001
DELIV-3 | DEVELOPMENT DELIVERABLES | Development deliverables | Development | Not Started | High | Tech Lead | 2025-07-03 | 2025-11-13
DEV-001 | Version-controlled Codebase | Set up Git repository and workflow | DevOps | Not Started | High | DevOps Engineer | 2025-07-03 | 2025-07-16 | SD-008
DEV-002 | Frontend Application | Develop complete frontend application | Development | Not Started | High | Frontend Developer | 2025-07-10 | 2025-10-15 | IM-001
DEV-003 | Serverless Functions | Implement serverless functions | Development | Not Started | High | Backend Developer | 2025-07-17 | 2025-10-08 | IM-004
DEV-004 | Database Schema and Migrations | Implement database schema and migrations | Development | Not Started | High | Database Engineer | 2025-07-10 | 2025-07-30 | SD-003
DEV-005 | API Implementation | Implement complete API | Development | Not Started | High | Backend Developer | 2025-09-12 | 2025-10-15 | IM-013
DEV-006 | Authentication System | Implement authentication system | Development | Not Started | High | Backend Developer | 2025-07-10 | 2025-07-30 | SD-006
DEV-007 | Unit and Integration Tests | Develop comprehensive test suite | Testing | Not Started | High | QA Engineer | 2025-07-17 | 2025-11-13 | IM-017
DEV-008 | Build and Deployment Pipelines | Set up build and deployment pipelines | DevOps | Not Started | High | DevOps Engineer | 2025-11-07 | 2025-11-27 | TS-006
DELIV-4 | DEPLOYMENT DELIVERABLES | Deployment deliverables | Deployment | Not Started | High | DevOps Engineer | 2025-06-27 | 2025-12-10
DPL-001 | Production Environment | Set up production environment | DevOps | Not Started | High | DevOps Engineer | 2025-11-21 | 2025-12-03 | DP-003
DPL-002 | Staging Environment | Set up staging environment | DevOps | Not Started | High | DevOps Engineer | 2025-11-14 | 2025-11-27 | DP-001
DPL-003 | Development Environment | Set up development environment | DevOps | Not Started | High | DevOps Engineer | 2025-06-27 | 2025-07-09 | SD-008
DPL-004 | Continuous Integration Pipeline | Set up CI pipeline | DevOps | Not Started | High | DevOps Engineer | 2025-11-07 | 2025-11-20 | TS-006
DPL-005 | Continuous Deployment Pipeline | Set up CD pipeline | DevOps | Not Started | High | DevOps Engineer | 2025-11-14 | 2025-11-27 | DPL-004
DPL-006 | Monitoring and Alerting Setup | Set up monitoring and alerting | DevOps | Not Started | Medium | DevOps Engineer | 2025-11-28 | 2025-12-10 | DP-007
DPL-007 | Backup and Restore Procedures | Document and implement backup procedures | DevOps | Not Started | Medium | DevOps Engineer | 2025-11-21 | 2025-12-03 | DPL-001
DPL-008 | Disaster Recovery Plan | Create disaster recovery plan | DevOps | Not Started | Medium | DevOps Engineer | 2025-11-21 | 2025-12-03 | DPL-001