## code
Task ID | Task Name | Task Description | Category | Phase | Requirement Reference | Priority | Status | Assignee | Dependencies | Notes | Estimated Effort (Days)
T001 | Define Project Scope & Goals | Finalize and document the precise scope, goals, and target audience based on the Project Overview section. | Project Management | 1. Requirements Analysis | Project Overview | High | Completed | Ahmed Rehan |  | Documentation review
T002 | Conduct Coolors.co Feature Analysis | Thoroughly analyze Coolors.co features as listed, verifying completeness and understanding functionality. | Project Management | 1. Requirements Analysis | Feature Analysis | High | Completed | Ahmed Rehan | T001
T003 | Document Functional Requirements (Palette Gen) | Detail all FRs for the Palette Generation System (FR1.x). | Requirements | 1. Requirements Analysis | FR1.1-FR1.8 | High | Completed | Ahmed Rehan | T002
T004 | Document Functional Requirements (Color Tools) | Detail all FRs for Color Manipulation Tools (FR2.x). | Requirements | 1. Requirements Analysis | FR2.1-FR2.8 | High | Completed | Ahmed Rehan | T002
T005 | Document Functional Requirements (User Accounts) | Detail all FRs for User Account Management (FR3.x). | Requirements | 1. Requirements Analysis | FR3.1-FR3.8 | High | Completed | Ahmed Rehan | T002
T006 | Document Functional Requirements (Palette Mgmt) | Detail all FRs for Palette Management (FR4.x). | Requirements | 1. Requirements Analysis | FR4.1-FR4.8 | High | Completed | Ahmed Rehan | T002
T007 | Document Functional Requirements (Export) | Detail all FRs for the Export System (FR5.x). | Requirements | 1. Requirements Analysis | FR5.1-FR5.8 | High | Completed | Ahmed Rehan | T002
T008 | Document Functional Requirements (Community) | Detail all FRs for Community Features (FR6.x). | Requirements | 1. Requirements Analysis | FR6.1-FR6.8 | Medium | Completed | Ahmed Rehan | T002
T009 | Document Functional Requirements (Exploration) | Detail all FRs for Exploration Tools (FR7.x). | Requirements | 1. Requirements Analysis | FR7.1-FR7.8 | Medium | Completed | Ahmed Rehan | T002
T010 | Document Functional Requirements (UI) | Detail all FRs for the User Interface (FR8.x). | Requirements | 1. Requirements Analysis | FR8.1-FR8.8 | High | Completed | Ahmed Rehan | T002
T011 | Document Functional Requirements (Integrations) | Detail all FRs for Integration Features (FR9.x). | Requirements | 1. Requirements Analysis | FR9.1-FR9.8 | Medium | Completed | Ahmed Rehan | T002
T012 | Document Non-Functional Requirements (Performance) | Detail all NFRs for Performance (NFR1.x). | Requirements | 1. Requirements Analysis | NFR1.1-NFR1.8 | High | Completed | Ahmed Rehan
T013 | Document Non-Functional Requirements (Accessibility) | Detail all NFRs for Accessibility (NFR2.x), specifically targeting WCAG 2.1 AAA. | Requirements | 1. Requirements Analysis | NFR2.1-NFR2.8 | Critical | Completed | Ahmed Rehan |  | WCAG 2.1 AAA is a core goal
T014 | Document Non-Functional Requirements (Security) | Detail all NFRs for Security (NFR3.x). | Requirements | 1. Requirements Analysis | NFR3.1-NFR3.8 | High | Completed | Ahmed Rehan
T015 | Document Non-Functional Requirements (Scalability) | Detail all NFRs for Scalability (NFR4.x). | Requirements | 1. Requirements Analysis | NFR4.1-NFR4.8 | Medium | Completed | Ahmed Rehan |  | Consider Zero-Cost constraints
T016 | Document Non-Functional Requirements (Usability) | Detail all NFRs for Usability (NFR5.x). | Requirements | 1. Requirements Analysis | NFR5.1-NFR5.8 | High | Completed | Ahmed Rehan
T017 | Document Non-Functional Requirements (SEO) | Detail all NFRs for SEO (NFR6.x). | Requirements | 1. Requirements Analysis | NFR6.1-NFR6.8 | High | Completed | Ahmed Rehan
T018 | Document Non-Functional Requirements (Compatibility) | Detail all NFRs for Compatibility (NFR7.x). | Requirements | 1. Requirements Analysis | NFR7.1-NFR7.8 | High | Completed | Ahmed Rehan
T019 | Document Non-Functional Requirements (Zero-Cost) | Detail all NFRs related to Zero-Cost Infrastructure (NFR8.x). | Requirements | 1. Requirements Analysis | NFR8.1-NFR8.8 | Critical | Completed | Ahmed Rehan |  | Core project constraint
T020 | Document Enhanced Features Requirements (List 1-12) | Detail requirements for each of the 12 enhanced features listed. | Requirements | 1. Requirements Analysis | Enhanced Features 1-12 | Medium | Completed | Ahmed Rehan |  | Prioritize based on feasibility/impact
T021 | Create Project Plan & Timeline | Develop the detailed project plan, resource allocation, and timeline based on Waterfall phases. | Project Management | 1. Requirements Analysis | Development Methodology | High | Completed | Ahmed Rehan | T001,T002,T003,T004,T005,T006,T007,T008,T009,T010,T011,T012,T013,T014,T015,T016,T017,T018,T019,T020
T022 | Conduct Risk Assessment | Identify and document risks (Technical, Business, Project Mgmt) and mitigation strategies. | Project Management | 1. Requirements Analysis | Risk Assessment | High | Completed | Ahmed Rehan | T001,T002,T003,T004,T005,T006,T007,T008,T009,T010,T011,T012,T013,T014,T015,T016,T017,T018,T019,T020
T023 | Select Technology Stack | Finalize the technology stack (Frontend, Backend, Database, Auth, etc.) based on requirements and zero-cost constraints. | System Design | 2. System Design | Technology Stack, NFR8 | High | Completed | Ahmed Rehan | T019 | Reference Appendix B
T024 | Design System Architecture | Document the overall system architecture (JAMstack, Serverless, Static Frontend). | System Design | 2. System Design | System Architecture | High | Completed | Ahmed Rehan | T023
T025 | Design Database Schema | Design the database schema for Supabase (GraphQL), considering scalability and query performance. | System Design | 2. System Design | Database Architecture, NFR4.3, NFR4.8 | High | Completed | Ahmed Rehan | T015,T023
T026 | Design API (GraphQL) | Design the GraphQL API schema, including queries, mutations, and types. Document endpoints. | System Design | 2. System Design | API Design | High | Completed | Ahmed Rehan | T023
T027 | Design Authentication Flow | Design the user authentication flow using Auth0 (email, social logins, password reset). | System Design | 2. System Design | User Authentication, FR3.x | High | Completed | Ahmed Rehan | T005,T023
T028 | Design UI/UX Wireframes & Prototypes | Create wireframes and interactive prototypes for all major screens and user flows. | UI/UX Design | 2. System Design | User Experience Design | High | In Progress | Ahmed Rehan | T010,T016
T029 | Design Accessibility Strategy | Plan specific implementation details for WCAG 2.1 AAA compliance (contrast, keyboard nav, ARIA). | UI/UX Design | 2. System Design | Accessibility Implementation, NFR2.1 | Critical | Completed | Ahmed Rehan | T013,T028
T030 | Design SEO Strategy Implementation | Plan specific implementation details for on-page, technical, and content SEO. | System Design | 2. System Design | SEO Strategy, NFR6 | High | Completed | Ahmed Rehan | T017
T031 | Design Zero-Cost Infrastructure Plan | Detail the specific services, configurations, and optimization strategies for zero-cost hosting. | System Design | 2. System Design | Zero-Cost Strategy, NFR8 | Critical | Completed | Ahmed Rehan | T019 | Reference Appendix D
T032 | Design Security Architecture | Plan security measures (HTTPS, hashing, CSRF, input sanitization, rate limiting, CSP). | System Design | 2. System Design | Security Requirements, NFR3 | High | Completed | Ahmed Rehan | T014
T033 | Set up Development Environment | Configure local development environments for frontend and backend. | Development | 3. Implementation | DevOps | High | Completed | Ahmed Rehan | T023
T034 | Set up Version Control (Git/GitHub) | Initialize Git repository on GitHub, establish branching strategy. | Development | 3. Implementation | DevOps | High | Not Started | Ahmed Rehan
T035 | Implement Frontend Framework (React/TS/Next.js) | Set up the basic React project structure with TypeScript and Next.js. | Frontend Dev | 3. Implementation | Technology Stack | High | Not Started | Ahmed Rehan | T023,T033
T036 | Implement State Management (Redux Toolkit) | Set up Redux Toolkit for global state management. | Frontend Dev | 3. Implementation | Technology Stack | High | Not Started | Ahmed Rehan | T035
T037 | Implement Styling (Tailwind CSS) | Integrate and configure Tailwind CSS for styling. | Frontend Dev | 3. Implementation | Technology Stack | High | Not Started | Ahmed Rehan | T035
T038 | Implement UI Component Library (Headless UI) | Integrate Headless UI for base accessible components. | Frontend Dev | 3. Implementation | Technology Stack, NFR2 | High | Not Started | Ahmed Rehan | T029,T035
T039 | Implement Color Processing Libraries (chroma.js, colord) | Integrate libraries for color manipulation and analysis. | Frontend Dev | 3. Implementation | Technology Stack | High | Not Started | Ahmed Rehan | T035
T040 | Implement Basic UI Layout & Navigation | Build the main application shell, global navigation, and routing. | Frontend Dev | 3. Implementation | FR8.x, UI Design | High | Not Started | Ahmed Rehan | T028,T035
T041 | Implement Random Palette Generation Logic | Develop the client-side logic for generating random palettes. | Frontend Dev | 3. Implementation | FR1.1,FR1.4 | High | Not Started | Ahmed Rehan | T039
T042 | Implement Palette Display UI | Create the UI for displaying color palettes (full-screen view). | Frontend Dev | 3. Implementation | FR1.1,FR8.4,UI Design | High | Not Started | Ahmed Rehan | T037,T038,T040
T043 | Implement Color Locking Feature | Add functionality to lock/unlock individual colors during generation. | Frontend Dev | 3. Implementation | FR1.2 | High | Not Started | Ahmed Rehan | T041,T042
T044 | Implement Space Bar Generation Shortcut | Add keyboard shortcut (Space bar) to generate new palettes. | Frontend Dev | 3. Implementation | FR1.3,FR8.1 | High | Not Started | Ahmed Rehan | T041,T042
T045 | Implement Color Adjustment Panel UI | Build the UI panel for adjusting HSL, RGB, Temp, etc. | Frontend Dev | 3. Implementation | FR2.1-FR2.5,FR8.5,UI Design | High | Not Started | Ahmed Rehan | T037,T038,T042
T046 | Implement Color Adjustment Logic | Develop the client-side logic for HSL, RGB, Temp adjustments. | Frontend Dev | 3. Implementation | FR2.1,FR2.2,FR2.3 | High | Not Started | Ahmed Rehan | T039,T045
T047 | Implement Color Input/Picker | Add functionality to input exact color values and use a color picker. | Frontend Dev | 3. Implementation | FR2.4,FR2.5 | High | Not Started | Ahmed Rehan | T045,T046
T048 | Implement Undo/Redo Functionality | Add undo/redo capabilities for palette changes. | Frontend Dev | 3. Implementation | FR1.7 | Medium | Not Started | Ahmed Rehan | T041,T046
T049 | Implement Palette Size Adjustment | Allow users to change the number of colors in the palette (3-10). | Frontend Dev | 3. Implementation | FR1.4 | Medium | Not Started | Ahmed Rehan | T041,T042
T050 | Set up Backend Serverless Functions (Vercel/Netlify) | Configure the serverless function environment. | Backend Dev | 3. Implementation | Technology Stack | High | Not Started | Ahmed Rehan | T023
T051 | Set up Database (Supabase) | Provision Supabase project, apply database schema. | Backend Dev | 3. Implementation | Technology Stack | High | Not Started | Ahmed Rehan | T023,T025
T052 | Set up Authentication (Auth0) | Configure Auth0 tenant, set up providers (Email, Google, FB, Twitter). | Backend Dev | 3. Implementation | Technology Stack | High | Not Started | Ahmed Rehan | T023,T027
T053 | Implement User Registration API/Function | Create backend logic for email registration and verification. | Backend Dev | 3. Implementation | FR3.1,FR3.8 | High | Not Started | Ahmed Rehan | T050,T051,T052
T054 | Implement User Login API/Function (Email & Social) | Create backend logic for email and social logins via Auth0. | Backend Dev | 3. Implementation | FR3.1,FR3.2 | High | Not Started | Ahmed Rehan | T050,T051,T052
T055 | Implement Password Reset API/Function | Create backend logic for password reset functionality. | Backend Dev | 3. Implementation | FR3.3 | High | Not Started | Ahmed Rehan | T050,T051,T052
T056 | Implement Session Management | Handle secure session/token management on backend and frontend. | Backend Dev | 3. Implementation | FR3.6,NFR3.6 | High | Not Started | Ahmed Rehan | T050,T054
T057 | Integrate Authentication with Frontend | Connect frontend UI to Auth0 for registration, login, logout flows. | Frontend Dev | 3. Implementation | FR3.x | High | Not Started | Ahmed Rehan | T040,T053,T054,T055,T056
T058 | Implement User Account Settings API/Function | Create backend logic for managing user profile data and settings. | Backend Dev | 3. Implementation | FR3.4,FR3.7 | Medium | Not Started | Ahmed Rehan | T050,T051,T056
T059 | Implement User Account Deletion API/Function | Create backend logic for user account deletion. | Backend Dev | 3. Implementation | FR3.5 | Medium | Not Started | Ahmed Rehan | T050,T051,T056
T060 | Implement Account Settings UI | Build the frontend UI for users to manage their profile and settings. | Frontend Dev | 3. Implementation | FR3.4,FR3.7,FR3.5 | Medium | Not Started | Ahmed Rehan | T040,T058,T059
T061 | Implement Save Palette API/Function | Create backend logic to save palettes to user accounts. | Backend Dev | 3. Implementation | FR4.1 | High | Not Started | Ahmed Rehan | T050,T051,T056
T062 | Implement Save Palette UI | Add button/functionality in the generator to save the current palette. | Frontend Dev | 3. Implementation | FR4.1 | High | Not Started | Ahmed Rehan | T042,T057,T061
T063 | Implement Palette Collections API/Function | Create backend logic for organizing palettes into collections/folders. | Backend Dev | 3. Implementation | FR4.2 | Medium | Not Started | Ahmed Rehan | T050,T051,T061
T064 | Implement Palette Tagging API/Function | Create backend logic for adding tags to palettes. | Backend Dev | 3. Implementation | FR4.3 | Medium | Not Started | Ahmed Rehan | T050,T051,T061
T065 | Implement Palette Search API/Function | Create backend logic for searching saved palettes (by name, tag, color). Consider Algolia integration. | Backend Dev | 3. Implementation | FR4.4 | Medium | Not Started | Ahmed Rehan | T050,T051,T061,T075 | Requires Algolia setup (T075)
T066 | Implement Palette Management UI (Dashboard) | Build the UI for users to view, search, organize (collections, tags), edit, and delete saved palettes. | Frontend Dev | 3. Implementation | FR4.1-FR4.6,UI Design | High | Not Started | Ahmed Rehan | T040,T061,T063,T064,T065
T067 | Implement Favorite/Star Palette Feature | Add functionality (API & UI) to mark palettes as favorites. | Full Stack | 3. Implementation | FR4.6 | Medium | Not Started | Ahmed Rehan | T061,T066
T068 | Implement Edit Saved Palette Feature | Add functionality (API & UI) to modify and re-save existing palettes. | Full Stack | 3. Implementation | FR4.5 | Medium | Not Started | Ahmed Rehan | T061,T066
T069 | Implement Generate Shareable URL | Develop functionality (backend/frontend) to create unique URLs for sharing palettes. | Full Stack | 3. Implementation | FR5.1 | High | Not Started | Ahmed Rehan | T061
T070 | Implement Copy Color Values Feature | Add UI buttons to copy color values in various formats (HEX, RGB, HSL, CMYK). | Frontend Dev | 3. Implementation | FR5.3 | High | Not Started | Ahmed Rehan | T042,T045
T071 | Implement Export Palette as Image (PNG/JPG) | Develop functionality (client-side or serverless) to generate image files of palettes. | Full Stack | 3. Implementation | FR5.2 | Medium | Not Started | Ahmed Rehan | T042
T072 | Implement Export Palette to Code Snippets (CSS/SCSS) | Develop functionality to generate CSS/SCSS code snippets from palettes. | Frontend Dev | 3. Implementation | FR5.5 | Medium | Not Started | Ahmed Rehan | T042
T073 | Implement Export Palette to PDF/ASE/SVG | Develop functionality (client-side or serverless) for advanced export formats. | Full Stack | 3. Implementation | FR5.4 | Medium | Not Started | Ahmed Rehan | T042 | May require libraries
T074 | Set up File Storage (Cloudinary) | Configure Cloudinary for storing user-uploaded images (for color extraction). | Backend Dev | 3. Implementation | Technology Stack | Medium | Not Started | Ahmed Rehan | T023
T075 | Set up Search (Algolia) | Configure Algolia for palette search functionality. | Backend Dev | 3. Implementation | Technology Stack | Medium | Not Started | Ahmed Rehan | T023
T076 | Implement Image Color Extraction | Develop functionality (API & UI) to upload an image and extract its dominant colors into a palette. | Full Stack | 3. Implementation | FR9.1 | Medium | Not Started | Ahmed Rehan | T074 | Requires color extraction library
T077 | Implement Dark/Light Mode Toggle | Add UI toggle and implement theme switching using Tailwind CSS. | Frontend Dev | 3. Implementation | FR8.3 | Medium | Not Started | Ahmed Rehan | T037,T040
T078 | Implement Responsive Design | Ensure all UI components and layouts are fully responsive across devices. | Frontend Dev | 3. Implementation | FR8.2,NFR7.1-NFR7.3 | High | Not Started | Ahmed Rehan | T040,T042,T066 | Ongoing task during UI dev
T079 | Implement Shades/Tints Generator | Add tool to generate shades and tints for a selected color. | Frontend Dev | 3. Implementation | FR2.6 | Medium | Not Started | Ahmed Rehan | T039,T045
T080 | Implement Contrast Checker | Add tool to check contrast ratios between colors in the palette, referencing WCAG standards. | Frontend Dev | 3. Implementation | FR2.7,Enhanced Features 1.2,NFR2.1 | High | Not Started | Ahmed Rehan | T039,T042
T081 | Implement Color Blindness Simulator | Add functionality to view palettes as they might appear with different types of color blindness. | Frontend Dev | 3. Implementation | FR2.8,Enhanced Features 1.1 | Medium | Not Started | Ahmed Rehan | T039,T042
T082 | Implement Trending Palettes Showcase | Develop mechanism (API & UI) to display popular/trending palettes. | Full Stack | 3. Implementation | FR6.1 | Medium | Not Started | Ahmed Rehan | T061 | Requires defining 'trending' logic
T083 | Implement Like/Comment/Follow Features | Develop backend (API) and frontend (UI) for community interactions. | Full Stack | 3. Implementation | FR6.2,FR6.3,FR6.4 | Medium | Not Started | Ahmed Rehan | T058,T061,T066,T163 | Requires moderation plan (T163)
T084 | Implement Public User Profiles | Develop public profile pages displaying user info and shared palettes. | Full Stack | 3. Implementation | FR6.5 | Medium | Not Started | Ahmed Rehan | T058,T061,T066
T085 | Implement Explore/Browse Palettes Feature | Develop UI and filtering logic for exploring palettes (by color, tag, popularity). | Full Stack | 3. Implementation | FR7.1,FR7.2 | Medium | Not Started | Ahmed Rehan | T061,T064,T065
T086 | Implement Basic SEO Structure | Implement semantic HTML, basic meta tags, and SEO-friendly URLs. | Frontend Dev | 3. Implementation | NFR6.1,NFR6.2,NFR6.4 | High | Not Started | Ahmed Rehan | T040 | Ongoing task during UI dev
T087 | Implement Basic Accessibility Features | Ensure keyboard navigation, focus management, and basic ARIA labels are implemented from the start. | Frontend Dev | 3. Implementation | NFR2.2,NFR2.4,NFR2.6 | Critical | Not Started | Ahmed Rehan | T038,T040 | Ongoing task during UI dev
T088 | Implement Basic Security Measures | Implement HTTPS, basic input sanitization, secure password storage (via Auth0). | Backend Dev | 3. Implementation | NFR3.1,NFR3.2,NFR3.4 | High | Not Started | Ahmed Rehan | T050,T052 | Ongoing task during backend dev
T089 | Implement Unit Testing Framework (Jest) | Set up Jest and React Testing Library for frontend unit tests. | Development | 3. Implementation | Testing Strategy | High | Not Started | Ahmed Rehan | T035
T090 | Write Unit Tests (Frontend) | Write unit tests for core components and logic (color manipulation, state management). | Frontend Dev | 3. Implementation | Testing Strategy | High | Not Started | Ahmed Rehan | T089 | Aim for 80% coverage
T091 | Write Unit Tests (Backend) | Write unit tests for serverless functions (mocking dependencies). | Backend Dev | 3. Implementation | Testing Strategy | High | Not Started | Ahmed Rehan | T050 | Aim for 80% coverage
T092 | Set up CI/CD Pipeline (GitHub Actions) | Configure GitHub Actions for automated testing and builds. | DevOps | 3. Implementation | DevOps, Deployment Plan | High | Not Started | Ahmed Rehan | T034
T093 | Implement AI Palette Generation (Keyword Based - Enhanced 1.1) | Develop initial AI feature: generate palettes based on keyword input. | AI/ML Dev | 3. Implementation | Enhanced Feature 1 | Medium | Not Started | Ahmed Rehan | T050,T061 | Requires AI model/API selection
T094 | Implement PWA Basics (Enhanced 12) | Set up Workbox, manifest file, and service worker for basic offline functionality. | Frontend Dev | 3. Implementation | Enhanced Feature 12 | Low | Not Started | Ahmed Rehan | T035
T095 | Set up Analytics (Plausible Self-Hosted) | Deploy and configure self-hosted Plausible Analytics instance. | DevOps | 3. Implementation | DevOps | Medium | Not Started | Ahmed Rehan |  | Requires hosting setup
T096 | Integrate Analytics Tracking | Add analytics tracking code to the frontend application. | Frontend Dev | 3. Implementation | DevOps | Medium | Not Started | Ahmed Rehan | T095
T097 | Set up Monitoring (Sentry) | Configure Sentry for error tracking (free tier). | DevOps | 3. Implementation | DevOps | Medium | Not Started | Ahmed Rehan | T023
T098 | Integrate Monitoring | Add Sentry SDK to frontend and backend for error reporting. | Full Stack | 3. Implementation | DevOps | Medium | Not Started | Ahmed Rehan | T097
T099 | Plan Integration Testing | Define strategy and scope for integration tests (API, service interactions). | Testing | 4. Testing | Testing Strategy | High | Not Started | Ahmed Rehan | T091
T100 | Execute Integration Testing | Perform tests verifying interactions between components, APIs, and database. | Testing | 4. Testing | Testing Strategy | High | Not Started | Ahmed Rehan | T099 | Requires implemented components
T101 | Plan System Testing | Define strategy and scope for end-to-end system tests (using Cypress). | Testing | 4. Testing | Testing Strategy | High | Not Started | Ahmed Rehan
T102 | Develop E2E Test Scripts (Cypress) | Write automated end-to-end test scripts for critical user flows. | Testing | 4. Testing | Testing Strategy | High | Not Started | Ahmed Rehan | T101 | Requires stable build
T103 | Execute System Testing | Run E2E tests across supported browsers and devices. | Testing | 4. Testing | Testing Strategy | High | Not Started | Ahmed Rehan | T102
T104 | Plan Performance Testing | Define strategy, tools, and metrics for performance testing (load, response times). | Testing | 4. Testing | Testing Strategy, NFR1 | High | Not Started | Ahmed Rehan | T012
T105 | Execute Performance Testing | Conduct performance tests under expected load conditions. Analyze results. | Testing | 4. Testing | Testing Strategy, NFR1 | High | Not Started | Ahmed Rehan | T104 | Requires stable build
T106 | Plan Security Testing | Define strategy for vulnerability scanning and penetration testing (manual/automated). | Testing | 4. Testing | Testing Strategy, NFR3 | High | Not Started | Ahmed Rehan | T014
T107 | Execute Security Testing | Perform security scans and manual checks for vulnerabilities. | Testing | 4. Testing | Testing Strategy, NFR3 | High | Not Started | Ahmed Rehan | T106 | Requires stable build
T108 | Plan Accessibility Testing (WCAG 2.1 AAA) | Define detailed testing procedures (automated, manual screen reader, keyboard). | Testing | 4. Testing | Testing Strategy, NFR2 | Critical | Not Started | Ahmed Rehan | T013,T029
T109 | Execute Automated Accessibility Testing (axe-core) | Run automated accessibility checks integrated into CI/CD or testing phase. | Testing | 4. Testing | Testing Strategy, NFR2 | Critical | Not Started | Ahmed Rehan | T108 | Requires stable build
T110 | Execute Manual Accessibility Testing | Perform manual checks using screen readers (NVDA, JAWS, VoiceOver), keyboard-only navigation, contrast tools. | Testing | 4. Testing | Testing Strategy, NFR2 | Critical | Not Started | Ahmed Rehan | T108 | Requires stable build
T111 | Plan Compatibility Testing | Define browser, device, and OS matrix for compatibility checks. | Testing | 4. Testing | Testing Strategy, NFR7 | High | Not Started | Ahmed Rehan | T018
T112 | Execute Compatibility Testing | Test application across the defined matrix. | Testing | 4. Testing | Testing Strategy, NFR7 | High | Not Started | Ahmed Rehan | T111 | Requires stable build
T113 | Conduct User Acceptance Testing (UAT) | Coordinate UAT with stakeholders/beta testers to validate requirements. | Testing | 4. Testing | Testing Strategy | High | Not Started | Ahmed Rehan |  | Requires stable build
T114 | Bug Fixing & Refinement | Address bugs identified during all testing phases. Refine UI/UX based on feedback. | Development | 4. Testing | Project Management | High | Not Started | Ahmed Rehan | T100,T103,T105,T107,T109,T110,T112,T113 | Ongoing during Testing phase
T115 | Finalize SEO Implementation | Implement advanced SEO techniques (structured data, sitemap, Core Web Vitals optimization). | Development | 4. Testing | SEO Strategy, NFR6 | High | Not Started | Ahmed Rehan | T086,T105 | Requires performance testing results (T105)
T116 | Optimize for Zero-Cost Limits | Review resource usage against free tier limits and implement final optimizations. | Development | 4. Testing | Zero-Cost Strategy, NFR8 | Critical | Not Started | Ahmed Rehan | T031,T105 | Requires monitoring data
T117 | Set up Staging Environment | Configure a production-like staging environment on Vercel/Netlify. | DevOps | 5. Deployment | Deployment Plan | High | Not Started | Ahmed Rehan | T092
T118 | Deploy to Staging | Deploy the tested application build to the staging environment. | DevOps | 5. Deployment | Deployment Plan | High | Not Started | Ahmed Rehan | T114,T117
T119 | Perform Staging Verification | Conduct smoke tests and final checks on the staging environment. | Testing | 5. Deployment | Deployment Plan | High | Not Started | Ahmed Rehan | T118
T120 | Prepare Production Environment | Configure production settings for hosting, database, auth, CDN. | DevOps | 5. Deployment | Deployment Plan | High | Not Started | Ahmed Rehan | T117
T121 | Finalize Deployment Checklist | Review and complete the pre-deployment checklist. | DevOps | 5. Deployment | Deployment Plan | High | Not Started | Ahmed Rehan | T119,T120
T122 | Execute Production Deployment | Deploy the application to the live production environment. | DevOps | 5. Deployment | Deployment Plan | Critical | Not Started | Ahmed Rehan | T121
T123 | Perform Post-Deployment Verification | Conduct smoke tests and critical path verification on production. Monitor initial performance and errors. | Testing | 5. Deployment | Deployment Plan | Critical | Not Started | Ahmed Rehan | T122
T124 | Develop Rollback Plan | Document the procedure for rolling back to a previous stable version if needed. | DevOps | 5. Deployment | Deployment Plan | High | Not Started | Ahmed Rehan
T125 | Finalize User Documentation | Complete user guides, FAQs, and help documentation. | Documentation | 5. Deployment | Appendices E | High | Not Started | Ahmed Rehan
T126 | Finalize Technical Documentation | Complete architecture, API, and maintenance documentation. | Documentation | 5. Deployment | Appendices E | High | Not Started | Ahmed Rehan
T127 | Implement Content Marketing Strategy | Start creating and publishing blog posts, guides, and resources based on SEO strategy. | Marketing | 6. Maintenance | Marketing Strategy | Medium | Not Started | Ahmed Rehan | T030
T128 | Implement Social Media Strategy | Set up social media profiles and begin regular posting schedule. | Marketing | 6. Maintenance | Marketing Strategy | Medium | Not Started | Ahmed Rehan
T129 | Implement Community Building Strategy | Engage in relevant forums, set up community support channels. | Marketing | 6. Maintenance | Marketing Strategy | Medium | Not Started | Ahmed Rehan
T130 | Establish Maintenance Procedures | Define processes for bug fixing, dependency updates, security patching, performance monitoring. | Project Management | 6. Maintenance | Maintenance Strategy | High | Not Started | Ahmed Rehan | T123
T131 | Monitor Free Tier Usage | Set up alerts and regularly monitor resource usage to stay within free limits. | DevOps | 6. Maintenance | Zero-Cost Strategy, NFR8 | Critical | Not Started | Ahmed Rehan | T116 | Ongoing task
T132 | Process User Feedback | Establish system for collecting, analyzing, and acting on user feedback and bug reports. | Project Management | 6. Maintenance | Maintenance Strategy | High | Not Started | Ahmed Rehan |  | Ongoing task
T133 | Plan Future Enhancements | Prioritize and plan implementation of remaining Enhanced Features based on feedback and resources. | Project Management | 6. Maintenance | Enhanced Features | Medium | Not Started | Ahmed Rehan | T132 | Ongoing task
T134 | Plan Monetization Strategy (Future) | Refine potential monetization options based on initial user adoption and feedback. | Project Management | 6. Maintenance | Monetization Strategy | Low | Not Started | Ahmed Rehan | T132 | For future consideration
T135 | Implement Color Harmony Rules Guidance | Develop UI/logic to suggest palettes based on color theory rules (complementary, analogous, etc.). | Frontend Dev | 3. Implementation | FR1.8,FR7.3 | Medium | Not Started | Ahmed Rehan | T039
T136 | Implement Color Psychology Information | Integrate content/data about color meanings and psychology accessible from the UI. | Content/Frontend | 3. Implementation | FR7.4 | Low | Not Started | Ahmed Rehan | T042 | Requires content creation
T137 | Implement Color Naming System | Integrate or develop a system to assign common names to colors. | Frontend Dev | 3. Implementation | FR7.5 | Low | Not Started | Ahmed Rehan | T039 | Could use existing libraries
T138 | Implement Drag-and-Drop Color Reordering | Add drag-and-drop functionality to reorder colors within the palette generator/display. | Frontend Dev | 3. Implementation | FR8.6 | Medium | Not Started | Ahmed Rehan | T042 | Requires DnD library
T139 | Implement Full-Screen Color View Details | Enhance the full-screen view with options and detailed color info panels. | Frontend Dev | 3. Implementation | FR8.4,FR8.5 | Medium | Not Started | Ahmed Rehan | T042
T140 | Implement Keyboard Shortcuts (Comprehensive) | Ensure all major actions have documented and functional keyboard shortcuts. | Frontend Dev | 3. Implementation | FR8.1 | High | Not Started | Ahmed Rehan | T044 | Review against FR list
T141 | Implement Browser Extension (Chrome - Initial) | Develop the core functionality for a Chrome extension (e.g., color picker, palette sync stub). | Integration Dev | 3. Implementation | FR9.2 | Low | Not Started | Ahmed Rehan |  | Enhanced Feature 4
T142 | Implement Figma Plugin (Initial) | Develop the basic structure and core functionality for a Figma plugin (e.g., export palette). | Integration Dev | 3. Implementation | FR9.3 | Low | Not Started | Ahmed Rehan |  | Requires Figma API knowledge
T143 | Implement Adobe Integration (Initial) | Research and plan initial Adobe integration (e.g., ASE export verification). | Integration Dev | 3. Implementation | FR9.3 | Low | Not Started | Ahmed Rehan | T073
T144 | Develop Public API (Basic Endpoints) | Implement initial public API endpoints for accessing public palettes or basic generation. | Backend Dev | 3. Implementation | FR5.6,FR9.4 | Low | Not Started | Ahmed Rehan | T026,T050 | Needs clear definition of free tier scope
T145 | Implement Palette Version History | Add backend logic and potentially UI elements to track changes to saved palettes. | Full Stack | 3. Implementation | FR4.7 | Low | Not Started | Ahmed Rehan | T061,T068 | Could be complex
T146 | Implement Bulk Operations for Palettes | Add UI functionality for selecting and performing actions (delete, tag, move) on multiple palettes. | Frontend Dev | 3. Implementation | FR4.8 | Low | Not Started | Ahmed Rehan | T066
T147 | Implement Social Media Sharing | Add buttons/links to share palettes directly to major social media platforms. | Frontend Dev | 3. Implementation | FR5.7 | Low | Not Started | Ahmed Rehan | T042,T069
T148 | Implement Reporting Functionality (Community) | Add UI and backend logic for users to report inappropriate palettes or comments. | Full Stack | 3. Implementation | FR6.8 | Medium | Not Started | Ahmed Rehan | T083,T163 | Requires moderation workflow (T163)
T149 | Implement Featured Collections Showcase | Develop UI and potentially admin tools to feature specific user collections. | Full Stack | 3. Implementation | FR6.6 | Low | Not Started | Ahmed Rehan | T063,T066
T150 | Implement User Activity Feeds | Develop backend logic and UI to display relevant activity (e.g., new palettes from followed users). | Full Stack | 3. Implementation | FR6.7 | Low | Not Started | Ahmed Rehan | T061,T083
T151 | Implement Palette Categorization (Themes) | Develop tagging/categorization system and UI for thematic browsing. | Full Stack | 3. Implementation | FR7.7 | Low | Not Started | Ahmed Rehan | T064,T085
T152 | Implement Seasonal/Trending Collections (Admin) | Create mechanism (likely admin-managed) to define and display seasonal/trending collections. | Full Stack | 3. Implementation | FR7.8 | Low | Not Started | Ahmed Rehan | T063 | Requires admin interface or manual DB updates
T153 | Implement Customizable UI Settings | Allow users to customize aspects of the UI (e.g., compact mode, display preferences). | Frontend Dev | 3. Implementation | FR8.7 | Low | Not Started | Ahmed Rehan | T040 | Requires defining customizable elements
T154 | Implement Multi-Language Support (i18n Structure) | Set up the internationalization framework (e.g., i18next) and structure for future language additions. | Frontend Dev | 3. Implementation | FR8.8,Enhanced Feature 11 | Low | Not Started | Ahmed Rehan | T035 | Initial setup, not full translation
T155 | Implement Palette Embedding | Develop functionality to generate embed codes for displaying palettes on external websites. | Full Stack | 3. Implementation | FR9.6 | Low | Not Started | Ahmed Rehan | T069 | Needs security considerations
T156 | Implement Advanced Contrast Checking (AAA) | Ensure contrast checker adheres strictly to WCAG 2.1 AAA requirements (7:1 ratio). | Frontend Dev | 3. Implementation | NFR2.1,NFR2.3 | Critical | Not Started | Ahmed Rehan | T080 | Accessibility Deep Dive
T157 | Implement ARIA Landmarks & Roles (Comprehensive) | Ensure all sections and interactive elements have appropriate ARIA landmarks and roles. | Frontend Dev | 3. Implementation | NFR2.4 | Critical | Not Started | Ahmed Rehan | T087 | Accessibility Deep Dive
T158 | Implement Text Alternatives (Alt Text) | Ensure all images and non-text content have meaningful text alternatives. | Frontend Dev | 3. Implementation | NFR2.7 | Critical | Not Started | Ahmed Rehan | T087 | Accessibility Deep Dive
T159 | Implement Focus Management (Modals/Dialogs) | Ensure focus is correctly managed (trapped, returned) for all modals, dialogs, and dynamic UI parts. | Frontend Dev | 3. Implementation | NFR2.6 | Critical | Not Started | Ahmed Rehan | T087 | Accessibility Deep Dive
T160 | Implement CSRF Protection | Ensure backend functions are protected against Cross-Site Request Forgery. | Backend Dev | 3. Implementation | NFR3.3 | High | Not Started | Ahmed Rehan | T050 | Usually handled by framework/libs
T161 | Implement Rate Limiting | Implement rate limiting on critical API endpoints (login, generation, etc.). | Backend Dev | 3. Implementation | NFR3.5 | Medium | Not Started | Ahmed Rehan | T050 | May depend on serverless provider features
T162 | Implement Content Security Policy (CSP) | Define and implement a strict Content Security Policy header. | DevOps/Backend | 3. Implementation | NFR3.7 | Medium | Not Started | Ahmed Rehan | T050,T117
T163 | Define Moderation Workflow | Document the process for handling reported community content (palettes, comments). | Project Management | 3. Implementation | FR6.8 | Medium | Not Started | Ahmed Rehan | T148
T164 | Implement XML Sitemap Generation | Set up automated XML sitemap generation (e.g., using next-sitemap). | DevOps/Frontend | 3. Implementation | NFR6.7,Technical SEO | High | Not Started | Ahmed Rehan | T086 | Requires build process integration
T165 | Implement Structured Data (JSON-LD) | Add JSON-LD schema markup for relevant content types (palettes, colors, articles). | Frontend Dev | 3. Implementation | NFR6.3,Technical SEO | High | Not Started | Ahmed Rehan | T086
T166 | Implement Canonical URLs | Ensure canonical URLs are correctly implemented for all pages, especially for shared/generated palettes. | Frontend Dev | 3. Implementation | NFR6.6,Technical SEO | High | Not Started | Ahmed Rehan | T086
T167 | Optimize Image Loading (Lazy Loading, Formats) | Implement lazy loading for images and use modern formats (e.g., WebP) where appropriate. | Frontend Dev | 3. Implementation | NFR1.7,NFR6.8,Technical SEO | High | Not Started | Ahmed Rehan | T086
T168 | Develop Onboarding Guidance | Create simple onboarding steps or tooltips for new users. | UI/UX Design | 3. Implementation | NFR5.7 | Medium | Not Started | Ahmed Rehan | T028
T169 | Plan Enhanced Features Implementation (Post-Launch) | Create a prioritized roadmap for implementing the remaining enhanced features after the initial launch. | Project Management | 4. Testing | Enhanced Features | Medium | Not Started | Ahmed Rehan | T020,T133
T170 | Write User Guide / Knowledge Base Content | Draft initial content for the self-service support documentation. | Documentation | 4. Testing | Support Strategy, Appendix E | Medium | Not Started | Ahmed Rehan | T125
T171 | Set up Community Forum (if applicable) | Choose and configure a platform for the community support forum (could be GitHub Discussions initially). | DevOps | 5. Deployment | Support Strategy | Low | Not Started | Ahmed Rehan |  | Free options preferred
T172 | Set up Support Email/System | Configure the support email address and potentially a simple ticketing system/tracker. | DevOps | 5. Deployment | Support Strategy | Medium | Not Started | Ahmed Rehan
T173 | Develop Marketing Content (Initial Batch) | Create the first set of blog posts/articles identified in the content strategy. | Marketing | 5. Deployment | Marketing Strategy | Medium | Not Started | Ahmed Rehan | T127
T174 | Finalize Brand Identity Assets | Create final logo, color scheme (ironic!), typography guidelines for AestheticPalettes itself. | UI/UX Design | 2. System Design | Appendix E | Medium | Not Started | Ahmed Rehan
T175 | Create UI Component Library Documentation | Document the usage and props for the reusable UI components created. | Documentation | 4. Testing | Appendix E | Medium | Not Started | Ahmed Rehan | T038
T176 | Finalize Competitive Analysis Document | Update Appendix A with any final insights before launch. | Documentation | 5. Deployment | Appendix A | Low | Not Started | Ahmed Rehan
T177 | Finalize Technology Evaluation Document | Update Appendix B based on final implementation choices. | Documentation | 5. Deployment | Appendix B | Low | Not Started | Ahmed Rehan | T023
T178 | Finalize Accessibility Implementation Details Document | Update Appendix C with specific techniques used. | Documentation | 5. Deployment | Appendix C | Medium | Not Started | Ahmed Rehan | T108,T109,T110
T179 | Finalize Zero-Cost Infrastructure Details Document | Update Appendix D based on final configurations and monitoring setup. | Documentation | 5. Deployment | Appendix D | Medium | Not Started | Ahmed Rehan | T116,T131
T180 | Finalize User Personas Document | Review and finalize user personas in Appendix F. | Documentation | 5. Deployment | Appendix F | Low | Not Started | Ahmed Rehan
T181 | Implement Analytics Dashboard (Enhanced 2 - Basic) | Set up basic reporting/views within Plausible (or other tool) for key metrics. | Analytics | 6. Maintenance | Enhanced Feature 2 | Low | Not Started | Ahmed Rehan | T095,T096 | Post-launch activity
T182 | Implement Advanced Accessibility Tool (Score - Enhanced 3) | Develop logic to provide an estimated accessibility score for generated palettes based on contrast. | Frontend Dev | 6. Maintenance | Enhanced Feature 3 | Low | Not Started | Ahmed Rehan | T080 | Post-launch activity
T183 | Implement Extended Browser Integration (Website Extractor - Enhanced 4) | Add functionality to the browser extension to extract palettes from the current webpage. | Integration Dev | 6. Maintenance | Enhanced Feature 4 | Low | Not Started | Ahmed Rehan | T141 | Post-launch activity
T184 | Implement Advanced Export Feature (Batch Export - Enhanced 5) | Allow users to select multiple saved palettes and export them together in a chosen format. | Full Stack | 6. Maintenance | Enhanced Feature 5 | Low | Not Started | Ahmed Rehan | T066,T071,T072,T073 | Post-launch activity
T185 | Implement Collaborative Feature (Team Workspaces - Basic) (Enhanced 6) | Design and implement basic structure for users to create teams/workspaces (may require paid tier pivot). | Full Stack | 6. Maintenance | Enhanced Feature 6 | Low | Not Started | Ahmed Rehan | T051,T058 | Post-launch, may conflict with zero-cost
T186 | Develop Educational Resource (Color Theory Tutorial - Enhanced 7) | Create an interactive color theory tutorial within the application. | Content/Frontend | 6. Maintenance | Enhanced Feature 7 | Low | Not Started | Ahmed Rehan | T135 | Post-launch activity
T187 | Implement Advanced Search (Image Search - Enhanced 8) | Allow users to upload an image to find visually similar palettes in the community library. | AI/ML Dev | 6. Maintenance | Enhanced Feature 8 | Low | Not Started | Ahmed Rehan | T065,T076 | Post-launch, requires image similarity tech
T188 | Develop Color Trend Analysis Report (Basic - Enhanced 9) | Analyze saved/liked palette data to produce a basic seasonal trend report (manual or semi-automated). | Analytics/Content | 6. Maintenance | Enhanced Feature 9 | Low | Not Started | Ahmed Rehan | T061,T082 | Post-launch activity
T189 | Implement Developer Tool (CSS Variable Gen - Enhanced 10) | Add option to export palette colors specifically as CSS custom properties. | Frontend Dev | 6. Maintenance | Enhanced Feature 10 | Low | Not Started | Ahmed Rehan | T072 | Post-launch activity
T190 | Implement Internationalization (Add Second Language - Enhanced 11) | Translate the UI into one additional language as a proof-of-concept. | Localization | 6. Maintenance | Enhanced Feature 11 | Low | Not Started | Ahmed Rehan | T154 | Post-launch activity
T191 | Implement PWA Offline Storage (Enhanced 12) | Enhance PWA to store user's saved palettes locally for offline access. | Frontend Dev | 6. Maintenance | Enhanced Feature 12 | Low | Not Started | Ahmed Rehan | T061,T094 | Post-launch activity
T192 | Conduct Post-Launch Review Meeting | Review launch metrics, user feedback, bug reports, and plan initial maintenance cycle. | Project Management | 6. Maintenance | Project Management | High | Not Started | Ahmed Rehan | T123,T132 | 1-2 weeks post-launch
T193 | Monitor Infrastructure Costs/Limits Closely | Continuously monitor usage of all free tier services to ensure compliance. | DevOps | 6. Maintenance | NFR8, Risk Assessment | Critical | Not Started | Ahmed Rehan | T131 | Ongoing task
T194 | Regular Dependency Updates | Schedule and perform regular updates of frontend and backend dependencies. | DevOps | 6. Maintenance | Maintenance Strategy | Medium | Not Started | Ahmed Rehan |  | Ongoing task
T195 | Regular Security Audits/Scans | Schedule and perform periodic security scans and reviews. | Security | 6. Maintenance | NFR3.8, Maintenance Strategy | Medium | Not Started | Ahmed Rehan |  | Ongoing task